## Instructions
ALAS Energy ¦ Portfolio Control Workbook
Weighted renewable project control model with checklist logic, risk adjustment, budget control, and geography rollups.
Step | Area | Explanation
1 | Update status | In Task_Tracker, switch Status between ☑ and ☐. Completion_Value updates automatically.
2 | Review timing | Planned_Date is the scheduled milestone. Actual_Date reflects realized completion for done tasks.
3 | Use controller KPIs | Portfolio_Master calculates Progress %, Total Delay Impact, Risk Factor, Risk-Adjusted Progress, Budget Used %, and Efficiency Index.
4 | Read geography rollups | Geography_Progress shows weighted progress by country first, then state, with progress bars.
5 | Present the story | Dashboard turns the tracker into a control tower view for interviews, outreach, or a reel.
Source note | Aligned to ILOS Energy's renewable project lifecycle and project control needs.
Note on B11: Public source URLs: https://www.ilos-energy.com/ and https://www.ilos-energy.com/career

## Task_Tracker
ALAS Energy ¦ Task Tracker
Weighted milestones with timing and delay logic. This is the engine that drives all portfolio, country, and state progress calculations.
Project_ID | Project_Name | Country | State | Task_Name | Stage | Owner | Status | Weight | Completion_Value | Planned_Date | Actual_Date | Delay_Days | Delay_Impact | Risk_Level | Critical_Flag
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-10-03 | 2025-10-03 | 0 | 0 | Low | No
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2025-11-12 | 2025-11-14 | 2 | 20 | Low | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2025-12-22 | 2025-12-27 | 5 | 60 | Medium | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2026-01-31 | 2026-02-03 | 3 | 18 | Low | No
P-101 | Brandenburg Solar Park | Germany | Brandenburg | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2026-03-12 | 2026-03-16 | 4 | 32 | Low | No
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Equipment Delivered | Construction | Supply Chain Lead | ☑ | 10 | 10 | 2026-05-01 | 2026-05-07 | 6 | 60 | Medium | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Installation Started | Construction | Site Manager | ☑ | 10 | 10 | 2026-05-21 | 2026-05-28 | 7 | 70 | Medium | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-06-30 |  | 0 | 0 | Low | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-07-20 |  | 0 | 0 | Low | Yes
P-101 | Brandenburg Solar Park | Germany | Brandenburg | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-07-30 |  | 0 | 0 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-11-19 | 2025-11-19 | 0 | 0 | Low | No
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2025-12-29 | 2025-12-29 | 0 | 0 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2026-02-07 | 2026-02-08 | 1 | 12 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2026-03-19 | 2026-03-21 | 2 | 12 | Low | No
P-102 | Andalusia Solar Cluster | Spain | Andalusia | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2026-04-28 | 2026-05-02 | 4 | 32 | Low | No
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Equipment Delivered | Construction | Supply Chain Lead | ☑ | 10 | 10 | 2026-06-17 | 2026-06-23 | 6 | 60 | Medium | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Installation Started | Construction | Site Manager | ☐ | 10 | 0 | 2026-07-07 |  | 0 | 0 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-08-16 |  | 0 | 0 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-09-05 |  | 0 | 0 | Low | Yes
P-102 | Andalusia Solar Cluster | Spain | Andalusia | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-09-15 |  | 0 | 0 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-12-14 | 2025-12-14 | 0 | 0 | Low | No
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2026-01-23 | 2026-01-24 | 1 | 10 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2026-03-04 | 2026-03-06 | 2 | 24 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2026-04-13 | 2026-04-14 | 1 | 6 | Low | No
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2026-05-23 | 2026-05-25 | 2 | 16 | Low | No
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Equipment Delivered | Construction | Supply Chain Lead | ☐ | 10 | 0 | 2026-07-12 |  | 0 | 0 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Installation Started | Construction | Site Manager | ☐ | 10 | 0 | 2026-08-01 |  | 0 | 0 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-09-10 |  | 0 | 0 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-09-30 |  | 0 | 0 | Low | Yes
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-10-10 |  | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-05-05 | 2025-05-05 | 0 | 0 | Low | No
P-104 | Occitanie Ground Mount | France | Occitanie | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2025-06-14 | 2025-06-14 | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2025-07-24 | 2025-07-24 | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2025-09-02 | 2025-09-02 | 0 | 0 | Low | No
P-104 | Occitanie Ground Mount | France | Occitanie | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2025-10-12 | 2025-10-14 | 2 | 16 | Low | No
P-104 | Occitanie Ground Mount | France | Occitanie | Equipment Delivered | Construction | Supply Chain Lead | ☑ | 10 | 10 | 2025-12-01 | 2025-12-02 | 1 | 10 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Installation Started | Construction | Site Manager | ☑ | 10 | 10 | 2025-12-21 | 2025-12-21 | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Installation Completed | Construction | Site Manager | ☑ | 12 | 12 | 2026-01-30 | 2026-01-30 | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Testing Completed | Commissioning | Commissioning Engineer | ☑ | 10 | 10 | 2026-02-19 | 2026-02-19 | 0 | 0 | Low | Yes
P-104 | Occitanie Ground Mount | France | Occitanie | Project Activated | Commissioning | Asset Manager | ☑ | 14 | 14 | 2026-03-01 | 2026-03-01 | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-10-24 | 2025-10-24 | 0 | 0 | Low | No
P-105 | North Holland Solar Farm | Netherlands | North Holland | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2025-12-03 | 2025-12-03 | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2026-01-12 | 2026-01-15 | 3 | 36 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Environmental Review Closed | Development | ESG & Compliance | ☐ | 6 | 0 | 2026-02-21 |  | 66 | 396 | High | No
P-105 | North Holland Solar Farm | Netherlands | North Holland | EPC Assigned | Construction | Construction Manager | ☐ | 8 | 0 | 2026-04-02 |  | 26 | 208 | High | No
P-105 | North Holland Solar Farm | Netherlands | North Holland | Equipment Delivered | Construction | Supply Chain Lead | ☐ | 10 | 0 | 2026-05-22 |  | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Installation Started | Construction | Site Manager | ☐ | 10 | 0 | 2026-06-11 |  | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-07-21 |  | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-08-10 |  | 0 | 0 | Low | Yes
P-105 | North Holland Solar Farm | Netherlands | North Holland | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-08-20 |  | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2026-01-09 | 2026-01-09 | 0 | 0 | Low | No
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2026-02-18 | 2026-02-18 | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2026-03-30 | 2026-03-31 | 1 | 12 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2026-05-09 | 2026-05-10 | 1 | 6 | Low | No
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2026-06-18 | 2026-06-20 | 2 | 16 | Low | No
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Equipment Delivered | Construction | Supply Chain Lead | ☐ | 10 | 0 | 2026-08-07 |  | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Installation Started | Construction | Site Manager | ☐ | 10 | 0 | 2026-08-27 |  | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-10-06 |  | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-10-26 |  | 0 | 0 | Low | Yes
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-11-05 |  | 0 | 0 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2026-02-18 | 2026-02-18 | 0 | 0 | Low | No
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2026-03-30 | 2026-03-31 | 1 | 10 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2026-05-09 | 2026-05-11 | 2 | 24 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2026-06-18 | 2026-06-20 | 2 | 12 | Low | No
P-107 | Saxony Battery-Ready PV | Germany | Saxony | EPC Assigned | Construction | Construction Manager | ☐ | 8 | 0 | 2026-07-28 |  | 0 | 0 | Low | No
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Equipment Delivered | Construction | Supply Chain Lead | ☐ | 10 | 0 | 2026-09-16 |  | 0 | 0 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Installation Started | Construction | Site Manager | ☐ | 10 | 0 | 2026-10-06 |  | 0 | 0 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Installation Completed | Construction | Site Manager | ☐ | 12 | 0 | 2026-11-15 |  | 0 | 0 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Testing Completed | Commissioning | Commissioning Engineer | ☐ | 10 | 0 | 2026-12-05 |  | 0 | 0 | Low | Yes
P-107 | Saxony Battery-Ready PV | Germany | Saxony | Project Activated | Commissioning | Asset Manager | ☐ | 14 | 0 | 2026-12-15 |  | 0 | 0 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Land Secured | Development | Development Lead | ☑ | 8 | 8 | 2025-04-16 | 2025-04-16 | 0 | 0 | Low | No
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Grid Connection Secured | Development | Grid Manager | ☑ | 10 | 10 | 2025-05-26 | 2025-05-26 | 0 | 0 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Permit Approved | Development | Permitting Manager | ☑ | 12 | 12 | 2025-07-05 | 2025-07-05 | 0 | 0 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Environmental Review Closed | Development | ESG & Compliance | ☑ | 6 | 6 | 2025-08-14 | 2025-08-14 | 0 | 0 | Low | No
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | EPC Assigned | Construction | Construction Manager | ☑ | 8 | 8 | 2025-09-23 | 2025-09-23 | 0 | 0 | Low | No
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Equipment Delivered | Construction | Supply Chain Lead | ☑ | 10 | 10 | 2025-11-12 | 2025-11-13 | 1 | 10 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Installation Started | Construction | Site Manager | ☑ | 10 | 10 | 2025-12-02 | 2025-12-03 | 1 | 10 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Installation Completed | Construction | Site Manager | ☑ | 12 | 12 | 2026-01-11 | 2026-01-11 | 0 | 0 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Testing Completed | Commissioning | Commissioning Engineer | ☑ | 10 | 10 | 2026-01-31 | 2026-01-31 | 0 | 0 | Low | Yes
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | Project Activated | Commissioning | Asset Manager | ☑ | 14 | 14 | 2026-02-10 | 2026-02-10 | 0 | 0 | Low | Yes
Formulas:
Delay_Days = IF([Status]="☑",MAX(0,[Actual_Date]-[Planned_Date]),MAX(0,TODAY()-[Planned_Date]))
Note on I4: Task weight reflects milestone importance. Higher weights represent more critical value-creating milestones.
Note on N4: Delay Impact = Delay_Days × Weight. A delay on a high-impact milestone matters more than a delay on a minor one.

## Portfolio_Master
ALAS Energy ¦ Portfolio Master
Project-level control logic for progress, delay impact, risk adjustment, and budget-performance comparison.
Project_ID | Project_Name | Country | State | Capacity_MW | Stage | Planned_COD | Completed_Weight | Total_Weight | Progress_% | Total_Delay_Impact | Avg_Delay_Days | Risk_Level | Risk_Factor | Risk_Adjusted_Progress | Budget_M€ | Actual_Cost_M€ | Budget_Used_% | Efficiency_Index | Budget_Alert
P-101 | Brandenburg Solar Park | Germany | Brandenburg | 145 | Development | 2026-07-30 | 64 | 100 | 64% | 260 | 2.7 | High | 75% | 48% | 120 | 114 | 95% | 67.37% | Over Budget
P-102 | Andalusia Solar Cluster | Spain | Andalusia | 220 | Construction | 2026-09-15 | 54 | 100 | 54% | 116 | 1.3 | Medium | 90% | 48.6% | 165 | 172 | 104.2% | 51.8% | Over Budget
P-103 | Sicily Agrivoltaic Hub | Italy | Sicily | 110 | Construction | 2026-10-10 | 44 | 100 | 44% | 56 | 0.6 | Medium | 90% | 39.6% | 94 | 98 | 104.3% | 42.2% | Over Budget
P-104 | Occitanie Ground Mount | France | Occitanie | 95 | Active | 2026-03-01 | 100 | 100 | 100% | 26 | 0.3 | Low | 100% | 100% | 82 | 81 | 98.78% | 101.2% | On Track
P-105 | North Holland Solar Farm | Netherlands | North Holland | 80 | Development | 2026-08-20 | 30 | 100 | 30% | 640 | 9.5 | High | 75% | 22.5% | 68 | 67 | 98.53% | 30.45% | Over Budget
P-106 | Lower Silesia PV Project | Poland | Lower Silesia | 130 | Construction | 2026-11-05 | 44 | 100 | 44% | 34 | 0.4 | Low | 100% | 44% | 101 | 108 | 106.9% | 41.15% | Over Budget
P-107 | Saxony Battery-Ready PV | Germany | Saxony | 160 | Development | 2026-12-15 | 36 | 100 | 36% | 46 | 0.5 | Medium | 90% | 32.4% | 126 | 123 | 97.62% | 36.88% | Over Budget
P-108 | Valencia Hybrid Solar Site | Spain | Valencia | 175 | Active | 2026-02-10 | 100 | 100 | 100% | 20 | 0.2 | Low | 100% | 100% | 136 | 134 | 98.53% | 101.5% | On Track

## Geography_Progress
ALAS Energy ¦ Geography Progress
Country Progress
Country | Projects | Completed_Weight | Total_Weight | Weighted_Progress_% | MW_Pipeline | Delayed_Projects | Progress_Bar
France | 1 | 100 | 100 | 100% | 95 | 0 | ████████████████████
Germany | 2 | 100 | 200 | 50% | 305 | 2 | ██████████
Italy | 1 | 44 | 100 | 44% | 110 | 1 | █████████
Netherlands | 1 | 30 | 100 | 30% | 80 | 1 | ██████
Poland | 1 | 44 | 100 | 44% | 130 | 0 | █████████
Spain | 2 | 154 | 200 | 77% | 395 | 1 | ███████████████
State / Region Progress
Country | State | Projects | Completed_Weight | Total_Weight | Weighted_Progress_% | MW_Pipeline | Delayed_Projects | Progress_Bar
France | Occitanie | 1 | 100 | 100 | 100% | 95 | 0 | ████████████████████
Germany | Brandenburg | 1 | 64 | 100 | 64% | 145 | 1 | █████████████
Germany | Saxony | 1 | 36 | 100 | 36% | 160 | 1 | ███████
Italy | Sicily | 1 | 44 | 100 | 44% | 110 | 1 | █████████
Netherlands | North Holland | 1 | 30 | 100 | 30% | 80 | 1 | ██████
Poland | Lower Silesia | 1 | 44 | 100 | 44% | 130 | 0 | █████████
Spain | Andalusia | 1 | 54 | 100 | 54% | 220 | 1 | ███████████
Spain | Valencia | 1 | 100 | 100 | 100% | 175 | 0 | ████████████████████

## Insights
ALAS Energy ¦ Controller Insights
Insight Area | Formula-Linked Statement | Use Case
Portfolio health | Portfolio weighted progress indicates meaningful execution risk remains | Dashboard summary
Delay focus | 2 projects show high risk based on delay impact and require management attention. | Escalation note
Budget pressure | 6 projects are consuming budget faster than weighted progress. | Controller commentary
Geography signal | France currently has the strongest weighted country-level progress. | Country spotlight
Project spotlight | Occitanie Ground Mount leads on risk-adjusted progress. | Management review

## Dashboard
ALAS Energy ¦ Portfolio Control Tower
Controller-level view of weighted progress, risk-adjusted performance, delay impact, budget efficiency, and geography progress.
Total Projects =COUNTA(Portfolio_Master!A5:A12) |  |  |  | MW Pipeline =SUM(Portfolio_Master!E5:E12) |  |  | Weighted Progress =AVERAGE(Portfolio_Master!J5:J12)
Risk-Adjusted Progress =AVERAGE(Portfolio_Master!O5:O12) |  |  |  | High Risk Projects =COUNTIF(Portfolio_Master!M5:M12,"High") |  |  | Over Budget Projects =COUNTIF(Portfolio_Master!T5:T12,"Over Budget")
Project | Progress_% | Risk_Adjusted_Progress | Budget_Used_% |  | Stage | Projects | Country | Weighted_Progress
Brandenburg Solar Park | 64% | 48% | 95% |  | Development | 3 | France | 100%
Andalusia Solar Cluster | 54% | 48.6% | 104.2% |  | Construction | 3 | Germany | 50%
Sicily Agrivoltaic Hub | 44% | 39.6% | 104.3% |  | Active | 2 | Italy | 44%
Occitanie Ground Mount | 100% | 100% | 98.78% |  |  |  | Netherlands | 30%
North Holland Solar Farm | 30% | 22.5% | 98.53% |  |  |  | Poland | 44%
Lower Silesia PV Project | 44% | 44% | 106.9% |  | Risk_Level | Projects | Spain | 77%
Saxony Battery-Ready PV | 36% | 32.4% | 97.62% |  | Low | 3
Valencia Hybrid Solar Site | 100% | 100% | 98.53% |  | Medium | 3
[5 empty] | High | 2